## Resource
RESOURCE LIST (10 pts)
# | RESOURCE | TYPE | UNIT COST (per hour) | COMMENTS
1 | roshanbhai patel | testing | 20 | Java
2 | Pallavi David | Development | 20 | C, C++, Java
3 | Navyasri Nimmala | Requirement/Design | 20 | Script, make, etc.
4 | Harish Annam | documentation | 20 | Automation
5 | Liang Zhao | Development | 20 | java
6 |  | Manager | 20

## Task Plan
TASK PLAN
WORK BREAK-DOWN STRUCTURE (20 pts) |  | ESTIMATION (20 pts) |  |  | ACTUAL COST |  | TASK PLANNING (20 pts) |  |  | TASK TRACKING
TASK | DELIVERABLES | DURATION (hours) | UNIT COST ($ per hr) | SUBTOTAL (Total $) | DURATION (hours) | SUBTOTAL (Total $) | PLANNED START DATE | PLANNED END DATE | ASSIGNED RESOURCE | ACTUAL START DATE | ACTUAL END DATE | STATUS
Planning
Requirement Document |  |  |  | #VALUE! |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
Definition & Architecture
Architecture (technology select) |  |  |  | #VALUE! |  | 0
|  |  |  | 0 |  | 0
0
|  |  |  | 0 |  | 0
Design & Development
Login Part |  |  |  | #VALUE! |  | 0
Login Page Design |  | 16 | 20 | #VALUE! |  | 0
Login Server-end Develop |  | 24 | 20 | #VALUE! |  | 0
Front-end and Server-end Combination |  | 16 | 20 | #VALUE! |  | 0
Main Listing part |  |  |  | #VALUE! |  | 0
Main Page Design |  | 16 | 20 | #VALUE! |  | 0
Main Page Server-end Develop |  | 24 | 20 | #VALUE! |  | 0
Front-end and Server-end Combination |  | 16 | 20 | #VALUE! |  | 0
Present Part |  |  |  | #VALUE! |  | 0
Present Page Design |  | 16 | 20 | #VALUE! |  | 0
Present Page Server-end Develop |  | 24 | 20 | #VALUE! |  | 0
Front-end and Server-end Combination |  | 16 | 20 | #VALUE! |  | 0
Add Part |  |  |  | #VALUE! |  | 0
Add Page Design |  | 16 | 20 | #VALUE! |  | 0
Add Page Server-end Develop |  | 24 | 20 | #VALUE! |  | 0
Front-end and Server-end Combination |  | 16 | 20 | #VALUE! |  | 0
Testing
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  | BUDGETED |  | ACTUAL
|  |  | Hours | Cost | Hours | Cost
|  |  | 240 | #VALUE! | 0 | 0

## Milestones
MILESTONES (20 pts)
# | KEY MILESTONES | STATUS | PLANNED DATE | ACTUAL DATE
Project Kick-off
1 | Project proposal Submission |  | Week of 06/09
2 | Project Plan Submission |  | Week of 06/16
Interim Milestones
5
6
7
8
9
10
11
12
Final Deliverables
13 | Project Due |  | Week of 08/10
14 | Class Presentation |  | Week of 08/10

## Risk
RISK PLANNING (10 pts)
# | RISK ITEM | PROP | SEVERITY | IMPACTS | MITIGATION PLAN
1 | Risk A |  | High | - Milestone #1
2 | Risk B |  | Medium | - Testing time
3 | Risk C |  | Low
4 |  |  | High
5

## Estimation
Wideband Delphi Estimation Worksheet
| Round 1 |  |  | Round 2 |  |  | Round 3 |  |  | Round 4 |  |  | Round 5
Tasks | Low | High | Delta | Low | High | Delta | Low | High | Delta | Low | High | Delta | Low | High | Delta