## Resource
RESOURCE LIST (10 pts)
# | RESOURCE | TYPE | UNIT COST (per hour) | COMMENTS
1 | Roshanbhai Patel 18137 | testing | 20 | Java
2 | Pallavi David 13402 | Development | 20 | C, C++, Java
3 | Navyasri Nimmala 18455 | Design | 20 | Script, make, etc.
4 | Harish Annam 13788 | documentation | 20 | Automation
5 | Liang Zhao 15247 | Development | 20 | java
6 | Sai Srujana 16434 | Manager | 20

## Task Plan
TASK PLAN
WORK BREAK-DOWN STRUCTURE (20 pts) |  | ESTIMATION (20 pts) |  |  | ACTUAL COST |  | TASK PLANNING (20 pts) |  |  | TASK TRACKING
TASK | DELIVERABLES | DURATION (hours) | UNIT COST ($ per hr) | SUBTOTAL (Total $) | DURATION (hours) | SUBTOTAL (Total $) | PLANNED START DATE | PLANNED END DATE | ASSIGNED RESOURCE | ACTUAL START DATE | ACTUAL END DATE | STATUS
Planning
Requirement Document |  |  |  | #VALUE! |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
Definition & Architecture
Requirement Documation |  | 40 | 20 | 800 |  | 0
Architecture (technology select) |  | 8 | 20 | 160 |  | 0
|  |  |  | 0 |  | 0
Design & Development
Design Page and Make Page Model |  | 56 | 20 | 1120 |  | 0
Development |  | 224 | 20 | 4480 |  | 0
Testing
Testing and bug fix |  | 80 | 20 | 160 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  | BUDGETED |  | ACTUAL
|  |  | Hours | Cost | Hours | Cost
|  |  | 100 | #VALUE! | 0 | 0

## Milestones
MILESTONES (20 pts)
# | KEY MILESTONES | STATUS | PLANNED DATE | ACTUAL DATE
Project Kick-off
1 | Project proposal Submission |  | Week of 01/11 | Week of 01/11
2 | Project Plan Submission |  | Week of 01/18 | Week of 01/18
Interim Milestones
3 | Requirement document completed |  | week of 01/25
4 | Architecture defined |  | week of 02/01 | week of 02/01
5 | Web page model has designed and completed |  | week of 02/01
6 | Web server programming completed |  | week of 02/22
7 | Integration of front-end and server-end finished |  | week of 02/29
8 | Test completed and all the bugs fixed |  | week of 03/14
9 | Deployment is completed |  | week of 03/21
Final Deliverables
10 | Project Due |  | Week of 04/11
11 | Class Presentation |  | Week of 04/11

## Risk
RISK PLANNING (10 pts)
# | RISK ITEM | PROP | SEVERITY | IMPACTS | MITIGATION PLAN
1 | Require Document dely |  | High | Milestone #4
2 | Project development delay |  | Medium | Testing time
3 | Deployment risks |  | Low | meet the due

## Estimation
Wideband Delphi Estimation Worksheet
| Round 1 |  |  | Round 2 |  |  | Round 3 |  |  | Round 4 |  |  | Round 5
Tasks | Low | High | Delta | Low | High | Delta | Low | High | Delta | Low | High | Delta | Low | High | Delta
Requirement Documation | 7 | 21 | 10 | 7 | 7 | 7
Architecture (technology select) | 7 | 7 | 7
Design Page and Make Page Model | 7 | 14 | 10 | 7 | 7 | 7
Development | 14 | 35 | 26 | 21 | 28 | 24 | 28 | 28 | 28
Testing | 7 | 21 | 15 | 14 | 14 | 14